Detailed Proposal for an Elementary School (Example: Green Valley Elementary)

1. Proposal Summary

Client: Green Valley Elementary (example)

Program: K–5 Robotics Foundations — turnkey classroom program using ESP32‑based starter kits, teacher training, and a 12‑month curriculum subscription.

Objective: Deliver hands‑on STEM learning that fits 45‑minute class periods, reduces teacher prep time, and produces measurable learning outcomes across grades K–5.

Recommended package: Classroom Rollout (3 classrooms) — scalable pilot that balances impact and budget.

2. Scope of Work (what we deliver)

Hardware

Starter Kit (per student group): ESP32 controller, chassis, motor drivers, 2 sensors (distance + line), OLED display, USB cable, spare parts kit.

Classroom Bundle (per classroom): 10 Starter Kits; storage caddy; charging/USB hub; spare parts pack.

Curriculum

Grade‑mapped modules: K–1 (Exploration & Patterns), 2–3 (Sensors & Motion), 4–5 (Programming Projects & Data).

Lesson format: 12 units per grade band; each unit = 45‑minute lesson + extension project.

Assessments: Short formative checks and one project rubric per unit.

Software & Platform

Teacher dashboard: Lesson distribution, student grouping, remote run/stop, basic analytics.

Code libraries: Copy‑paste examples (block + Python) with reproducible outcomes.

Secure relay: Safe remote access for teacher oversight during hybrid lessons.

Training & Support

On‑site training: One full‑day teacher workshop (up to 6 teachers) covering assembly, classroom management, and lesson delivery.

Follow‑up: Two 90‑minute virtual coaching sessions in months 1 and 3.

Support: Email support and educator forum; monthly resource updates.

Implementation

Pilot delivery: 3 classrooms (30 kits total) over 3 months with feedback loop and pilot report.

Scale plan: Option to expand to additional classrooms after pilot with volume discounts.

3. Timeline & Milestones

Week 0–2 — Contract & Prep

• Finalize scope, confirm PO, schedule training date, ship kits.

Week 3 — On‑site Training & Setup

• Deliver kits; run full‑day teacher workshop; teachers complete first sample lesson.

Weeks 4–12 — Pilot Execution

• Teachers run 4–6 lessons per classroom; weekly check‑ins; collect feedback and student work.

Week 13 — Pilot Report

• Deliver pilot report with teacher feedback, student outcomes, recommended adjustments.

Month 4–12 — Rollout & Support

• Implement curriculum across agreed grades; monthly webinars; analytics review at month 6 and 12.

4. Pricing (example for 3‑classroom pilot)

One‑time hardware & setup

• Classroom Bundle (10 kits) × 3 = 30 kits → $2,700 ($90 per kit bulk price)

• Storage & charging hardware = $300

• Shipping & handling = $200

Training & implementation

• On‑site full‑day workshop = $1,200

• Two virtual coaching sessions = $400

Curriculum & platform

• 12‑month curriculum subscription (per classroom) × 3 = $540 ($15/classroom/month)

• Teacher dashboard setup & secure relay = $360 (one‑time)

Pilot support & reporting

• Pilot coordination, data collection, pilot report = $600

Total Pilot Price (example) = $6,300

Payment terms: 50% on contract ($3,150), 40% on delivery ($2,520), 10% on pilot completion ($630). Institutional net‑30 available on request.

Notes: Prices are illustrative and can be adjusted for district volume discounts, local taxes, or custom add‑ons (camera, LIDAR, extended support).

5. Success Metrics & Reporting

Primary metrics

• Adoption: % of scheduled lessons delivered per classroom.

• Engagement: Average lesson completion rate and number of student projects submitted.

• Learning outcomes: Pre/post assessment improvement (target +20% average).

• Teacher readiness: Teacher confidence score (survey) target ≥ 4/5.

Reporting cadence

• Weekly: Short teacher check‑ins during pilot.

• End of pilot: Full pilot report with sample student work, rubric scores, and recommendations.

• Quarterly (post‑pilot): Analytics summary and suggested curriculum adjustments.

6. Next Steps (recommended)

1. Approve pilot and confirm package (we’ll assume 3 classrooms unless you specify otherwise).

2. Sign agreement / issue PO to lock training dates and manufacturing slot.

3. Schedule training and provide teacher list and preferred dates.

4. Receive kits and run on‑site training; begin pilot within 2–3 weeks of PO.

Prepared by: [Your Company Name] — replace placeholders with your organization details.